## Foglio1
Task | Description | Partner(s) Responsible(s) | OUTPUTS | due month | Semester 1 | [5 empty] | Semester 2 | [5 empty] | Semester 3 | [5 empty] | Semester 4
C 1 | Implementation of MSP |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
C1.1 | Initial Assesment | CORILA |  | 9 | bar: Semester 1 1 to Semester 2 9
C1.1.1 | Develop a basin scale analysis strongly MSP oriented | NTUA/UTH and will have the contribution of all partners, excepting UoA. | Summary on the existing knowledge on the Eastern Mediterranean area in its marine aspects relevant for MSP, particularly on cross-border issues | 9 | bar: Semester 1 1 to Semester 2 9
C1.1.2 | Ensuring region-wide coherence, building on the Barcelona Convention and its Protocols, processes, decisions, in relation to the definition and application of MSP in a systematic manner | UNEP MAP (PAP-RAC), with the participation of CORILA, MATTM, YPEN, NTUA, UTH | Recommendation and guidelines for a common understanding on a regional scale and specifically for the Eastern Mediterranean on MSP. A focus will be on transboundary issues, on available knowledge and on common starting points, taking also into account the ongoing work on MSP in the Barcelona Convention | 9 | bar: Semester 1 1 to Semester 1 6
C1.1.3 | Develop and propose a conceptual methodology for transboundary MSP aspects | NTUA/UTH, with the participation of CORILA, YPEN, RRC, CISD. | Recommendations and guidelines on the procedural steps to follow for the development of cross-border MSP, including a common understanding of Ecosystem-based approach | 6 | bar: Semester 1 1 to Semester 1 6
C1.2 | Development of cooperation on maritime spatial planning | UNEP-MAP |  | 24
C1.2.1 | Analysis on common objectives at sea level basin for crossborder cooperation | CORILA with the participation of all partners and with the collaboration of relevant stakeholders selected by the Stakeholder Panel | Overview on common objectives at sea basin level, taking into account a common view of the ecosystem-based approach | 10 | bar: Semester 1 1 to Semester 2 10
C1.2.2 | Establish a mechanism for a permanent and operational networking (Regional MSP Platform) among Member States in the area | UNEP-MAP (INFO-RAC), with the participation of all partners excepting UoA and with the collaboration of relevant stakeholders selected by the Stakeholder Panel | SUPREME cooperation platform and connected analysis of networking instruments | 17 | bar: Semester 2 8 to Semester 4 12
C1.3 | Support for Member States' implementation of Maritime Spatial Planning | Ministry of Environment and Energy of Greece |  | 20 | bar: Semester 1 5 to Semester 4 12
C1.3.1 | Spatial demands, future trends for maritime sectors and related cumulative impacts | MIT with the participation of CORILA, YPEN, NTUA, UTH, RRC, CISD | Report on trends on maritime sectors, considering current state and potential future spatial requirements, based on the best available spatial information. Potential cumulative impacts will be reported, too | 13 | bar: Semester 1 6 to Semester 3 6
C1.3.2 | Data and information requirements for MSP | CORILA, with the participation of all partners excepting UoA and a specifically of UNEP-MAP (INFO/RAC) | Report including: Analysis of data needs and existing data gaps in relation to a trasboudary perspective on MSP in the Eastern Mediterranean/ Barriers in overcoming data gaps and reach interoperability / Identification of a series of actions to be taken to overcome data gaps / Guidelines for data management and interoperability / Analysis of existing data portals and swot analysis for implementing interoperability / Analysis of existing data policies and proposed best practices to improve data exchange and reuse. | 18 | bar: Semester 1 6 to Semester 4 11
C1.3.3 | Tools and methods supporting MSP process | CORILA with the participation of MATTM, YPEN, NTUA, UTH and UNEP-MAP (PAP/RAC) | Report including: Analysis of existing tools to support MSP process / Barriers and opportunities in the interoperability of tools / Data needs at different scales to support the operationalization of MSP in Member States / Testing tools in the selected areas to demonstrate data needs and integration method to inform MSP process. | 12 | bar: Semester 2 12 to Semester 4 11
C1.3.4 | Stakeholders involvement and participation | UNEP-MAP with the participation of CORILA, YPEN, NTUA, UTH, UoA, RRC and CISD and with the collaboration of relevant stakeholders selected by the Stakeholder Panel | Report on potential approaches for stakeholder engagement on MSP and the evaluation of the outcome of stakeholder involvement in the pilot areas. | 19 | bar: Semester 1 6 to Semester 4 12
C1.3.5 | Definition of the most appropriate geographical scale for MSP plans at national scale | MATTM with the participation of CORILA, MIT, YPEN, NTUA, UTH, RRC and CISD | Recommendations on the most appropriate geographical scale for MSP plans in the area of reference | 7 | bar: Semester 1 5 to Semester 2 11
C1.3.6. | Coordination of sectorial policies | MIT, with the participation of all partners excepting UoA. | Recommendation for a synergic implementation of the regionally relevant policy instruments supporting the MSP implementation | 7 | bar: Semester 1 5 to Semester 2 11
C1.3.7 | Land – sea interactions and relationships with Integrated Coastal Zone Management (ICZM) | UNEP-MAP with the participation of CORILA, MATTM, YPEN, NTUA, UTH and RRC | Recommendation on how to perform a correct analysis of land-sea interactions, combining MSP and ICM in the considered project area, starting from selected case studies | 17 | bar: Semester 1 6 to Semester 4 10
C1.3.8 | Addressing MSP Implementation in Case Study Areas | CISD, with the participation of all partners excepting UoA | Five case study reports with recommendations, analyses and conclusions that can be taken into account in MSs relevant plans plus lessons learned for transfer to other locations and Member States. | 19 | bar: Semester 1 6 to Semester 4 12
| Case Study #1 : Northern Adriatic (Italy) | MIT
| Case Study #2 : The Dubrovnik-Neretva County | CISD
| Case Study #3 Slovenian coast: MSP – ICZM interaction | RCC
| Case Study #5 : Aegean (Greece) | YPEN
C 1.4 | Evaluation of the maritime spatial planning process | NTUA/UTH, with the participation of CORILA and YPEN. |  | 9 | bar: Semester 2 12 to Semester 4 8
C2 | Management and coordination
C2.1 | Establish a Steering Committee |  |  | 2 | bar: Semester 1 1 to Semester 1 2
C2.2 | Establish a Project Group |  |  | 2 | bar: Semester 1 1 to Semester 1 2
C2.3 | Establish a Stakeholder Panel |  |  | 24
C2.4 | Project schedule, Meetings and Reports |  |  | 24
C2.5 | Communication flow |  |  | 24
C3 | Communication and Dissemination
C3.1 | Coordinated visual identity |  |  | 4 | bar: Semester 1 1 to Semester 1 4
C3.2 | Project web portal |  |  | 24
C3.3 | Leaflets and newsletters, final booklet |  |  | 6,12,18 & 22-24 | bar: Semester 1 6; Semester 2 12; Semester 3 6; Semester 4 10 to Semester 4 12
C3.4 | Launching and Closing Conferences |  |  | 2 & 23 | bar: Semester 1 2; Semester 4 11
C3.5 | Participation in other events |  |  | 2-23
C3.6 | Articles in Scientific Journals |  |  | 22-24 | bar: Semester 4 10 to Semester 4 12